## Output Columns
Column Name | Description | Source / Calculation
WorkItemId | Azure DevOps Feature ID. Unique identifier for the milestone. | Direct from _MilestoneData[WorkItemId]
Title | Milestone name as recorded in Azure DevOps. | Direct from _MilestoneData[Title]
OriginalEndDate_PMP | Originally planned completion date at PMP baseline. | Direct from _MilestoneData[OriginalEndDate_PMP]
TargetEndDate | Current planned completion date. Reflects any schedule changes since baseline. | Direct from _MilestoneData[TargetEndDate]
Status | Current milestone state in Azure DevOps (e.g. Active, Done). | Direct from _MilestoneData[Status]
IsCriticalDate | Whether this milestone represents a critical date commitment (Yes/No). | Direct from _MilestoneData[IsCriticalDate]
IsKeyMilestone | Whether this milestone is flagged as a key milestone (Yes/No). | Direct from _MilestoneData[IsKeyMilestone]

## Filter Controls
Cell | Filter | Options | Logic
B2 | Financial Year | All, FY23-24, FY24-25, FY25-26, FY26-27 | Australian FY (Jul–Jun). Derived from date using IF(MONTH>=7, current/next year, previous/current year). Hardcoded list via Data Validation.
D2 | Month | All, Jan, Feb, Mar, Apr, May, Jun, Jul, Aug, Sep, Oct, Nov, Dec | Calendar month number matched via MATCH against {"Jan","Feb",...,"Dec"}. Dropdown can be displayed in any order.
F2 | Project (Area Path) | All, plus Area Path values | Contains match using ISNUMBER(SEARCH()) to support AreaPath/AreaPath2 hierarchies. Substring match, not exact.

## Inclusion Logic
Rule | Description
PMP Only | Only milestones where IsPMPMilestone = "Yes" are included. Non-PMP milestones are excluded regardless of other filter selections.
Year Match | Milestone appears if ANY of: TargetEndDate, OriginalEndDate_PMP, or completion date (for Done items) falls within the selected financial year (Jul–Jun).
Month Match | Milestone appears if ANY of: TargetEndDate, OriginalEndDate_PMP, or completion date (for Done items) falls within the selected calendar month.
Delayed Milestones | Captured by OR logic in the year and month filters. If OriginalEndDate_PMP falls in the selected period but TargetEndDate has moved to a later date, the milestone still appears in the original period.
Completed Milestones | Milestones with Status = "Done" are included if LastUpdated falls within the selected period. LastUpdated is used as a proxy for completion date since no dedicated CompletedDate field exists.
Filter Combination | All three filters (Year, Month, Project) combine with AND logic. Within the Year and Month filters, the three date conditions (target, original, completed) combine with OR logic.
Sort Order | Results sorted by TargetEndDate ascending (chronological). This is column 4 in the CHOOSECOLS output.
No Results | Displays "No milestones match filters" when no rows match the active filter combination. Prevents #CALC! error from FILTER returning empty.